## PROJECT DETAILS
PROJECT NAME | Hire Hub
Project Members | Joud AL-SHAHRANI
Jadel Alsaeri
Albandri Alsaadoon
Ghada Altemyat
DATE | 2025-10-13

## WEEK 1
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you you do yesterday? | (Sprint Start) No work recorded for the previous day. | Yesterday Joud worked on the Registration Form UI | Yesterday, she completed the registration setup | Yesterday, she built the Education Section | Yesterday, she was testing
| What are doing today? | Started working on the registration form UI and password reset testing. | Continued with registration form development and began implementing email validation. | Focused on the Education Section for the Job Seeker profile | Tested the Education Section and fixed minor bugs in the registration UI. | Completed integration of the Education Section with the main system.
| Is there anything blocking you? | Everything went smoothly. | No major issues. | some slow progress due to task coordination. | No major issues. | Everything went smoothly.
Jadel | What did you you do yesterday? | (Sprint Start) No work recorded for the previous day. | Yesterday, Jadel designed the database schema | Yesterday, she completed the setup | Yesterday, she worked on email testing | Yesterday, she developed the Personal Info Section
| What are doing today? | Designed the user database schema and started setting up the registration API. | Completed the database setup | Tested the email-sending service | Worked on the “Personal Info Section” for the job seeker profile. | Finished testing for the section developed earlier.
| Is there anything blocking you? | Everything went smoothly. | No major issues. | Everything went smoothly. | No major issues. | Incomplete validation or UI inconsistencies.
Ghada | What did you you do yesterday? | (Sprint Start) No work recorded for the previous day. | Yesterday, Ghada designed Login and Password Reset pages | Yesterday, she set up authentication | Yesterday, she worked on the Work Experience Section | Yesterday, she designed the page
| What are doing today? | Designed the Login Page and Password Reset Page. | Implemented authentication logic successfully. | Added the “Work Experience Section” to the Job Seeker profile. | Worked on the Job Posting Page design. | Completed development of the Rich Text Editor for job posts.
| Is there anything blocking you? | Everything went smoothly. | No major issues. | No major issues. | Layout inconsistency between sections. | Everything went smoothly.
Albandri | What did you you do yesterday? | (Sprint Start) No work recorded for the previous day. | Yesterday, Albandri handled Session Managemen. | Yesterday, she worked on Remember Me | Yesterday, she developed the reset system. | Yesterday, she worked on the indicator.
| What are doing today? | Set up session management for user login. | Implemented the “Remember Me” feature. | Started work on the Reset Token System for password recovery. | Added the Profile Completion Indicator feature. | Began developing the Basic Job Search algorithm.
| Is there anything blocking you? | Everything went smoothly. | No major issues. | Everything went smoothly. | Wrong calculation or missing progress tracking | Everything went smoothly.

## WEEK 2
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you you do yesterday? | Break | Reviewed backlog items | Completed login page | Tested login page | Fixed UI bugs
| What are doing today? | Updated product backlog | Started developing login page | Testing login page | Fixing minor UI bugs | Final review before sprint review
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers
Jadel | What did you you do yesterday? | Break | Reviewed sprint goals | Developed API endpoints | Integrated API | Tested data flow
| What are doing today? | Updated product backlog | Developing API endpoints | Integrating API with frontend | Testing data flow between API and frontend | Assisting with code cleanup
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers
Ghada | What did you you do yesterday? | Break | Reviewed backlog tasks | Wrote setup documentation | Created database schema | Tested database
| What are doing today? | Updated product backlog | Writing documentation for setup | Creating database schema | Testing database connection | Supporting team documentation
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers
Albandri | What did you you do yesterday? | Break | Helped refine user stories | Finished UI layout | Designed dashboard page | Implemented dashboard
| What are doing today? | Updated product backlog | Working on UI layout | Designing dashboard page | Implementing dashboard | Preparing presentation slides
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers

## WEEK 3
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you you do yesterday? | Break | Reviewed sprint 2 feedback | Developed user profile page | Tested user profile functions | Fixed validation errors
| What are doing today? | Updated product backlog | Started working on user profile page | Testing user profile functions | Fixing validation errors | Preparing sprint demo
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers
Jadel | What did you you do yesterday? | Break | Checked API performance | Improved API speed | Tested user profile functions | Tested API security
| What are doing today? | Updated product backlog | Enhancing API response time | Testing user profile functions | Testing API security | Helping prepare sprint demo
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers
Ghada | What did you you do yesterday? | Break | Reviewed documentation | Wrote test cases | Executed functional testing | Completed documentation
| What are doing today? | Updated product backlog | Creating new test cases | Executing functional testing | Writing sprint documentation | Reviewing sprint tasks
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers
Albandri | What did you you do yesterday? | Break | Updated UI elements | Created navigation menu | Tested navigation menu | Refined UI design
| What are doing today? | Updated product backlog | Working on navigation menu | Testing menu responsiveness | Refining design based on feedback | Finalizing user interface
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers

## WEEK 4
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you you do yesterday? | Break | Reviewed backlog items | Enhanced user profile page | Enhanced user profile page | Enhanced user profile page
| What are doing today? | Updated product backlog | Enhancing user profile page | Enhancing user profile page | Enhancing user profile page | Checked API performance
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers
Jadel | What did you you do yesterday? | Break | Reviewed backlog items | Tested user profile functions | Tested user profile functions | Tested user profile functions
| What are doing today? | Updated product backlog | Testing user profile functions | Testing user profile functions | Testing user profile functions | Checked API performance
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers
Jadel | What did you you do yesterday? | Break | Reviewed backlog items | Test user profile functions | Test user profile functions | Test user profile functions
| What are doing today? | Updated product backlog | Testing user profile functions | Testing user profile functions | Testing user profile functions | Checked API performance
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers
Ghada | What did you you do yesterday? | Break | Reviewed backlog items | Test user profile functions | Test user profile functions | Test user profile functions
| What are doing today? | Updated product backlog | Testing user profile functions | Testing user profile functions | Testing user profile functions | Checked API performance
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers
Albandri | What did you you do yesterday? | Break | Reviewed backlog items | Test user profile functions | Test user profile functions | Test user profile functions
| What are doing today? | Updated product backlog | Testing user profile functions | Testing user profile functions | Testing user profile functions | Checked API performance
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers

## WEEK 5
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you you do yesterday? | Break | Make sure we apply INVEST | Updated UI elements | Refined UI design | Refining design based on feedback
| What are doing today? | Make sure we apply INVEST | Updated UI elements | Refined UI design | Refining design based on feedback | Integrating API with frontend
| Is there anything blocking you? | Everything went smoothly. | Everything went smoothly. | Everything went smoothly. | Everything went smoothly. | Everything went smoothly.
Jadel | What did you you do yesterday? | Break | Make sure we apply INVEST | Updated UI elements | Refined UI design | Refining design based on feedback
| What are doing today? | Make sure we apply INVEST | Updated UI elements | Refined UI design | Refining design based on feedback | Integrating API with frontend
| Is there anything blocking you? | No major issues. | No major issues. | No major issues. | No major issues. | No major issues.
Ghada | What did you you do yesterday? | Break | Make sure we apply INVEST | Updated UI elements | Refined UI design | Refining design based on feedback
| What are doing today? | Make sure we apply INVEST | Updated UI elements | Refined UI design | Refining design based on feedback | Integrating API with frontend
| Is there anything blocking you? | Everything went smoothly. | Everything went smoothly. | Everything went smoothly. | Everything went smoothly. | Everything went smoothly.
Albandri | What did you you do yesterday? | Break | Make sure we apply INVEST | Updated UI elements | Refined UI design | Refining design based on feedback
| What are doing today? | Make sure we apply INVEST | Updated UI elements | Refined UI design | Refining design based on feedback | Integrating API with frontend
| Is there anything blocking you? | No major issues. | No major issues. | No major issues. | No major issues. | No major issues.

## WEEK 6
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Joud | What did you you do yesterday? | Break | Tested navigation menu | Tested navigation menu | Tested navigation menu | Tested data flow
| What are doing today? | Enhancing navigation menu | Enhancing navigation menu | Test navigation menu | Test data flow | Complet documentation
| Is there anything blocking you? | No blockers | No blockers | No blockers | No blockers | No blockers
Jadel | What did you you do yesterday? | Break | Enhanced navigation menu | Enhanced navigation menu | Tested navigation menu | Tested data flow
| What are doing today? | Enhancing navigation menu | Enhancing navigation menu | Test navigation menu | Test data flow | Complet documentation
| Is there anything blocking you? | Everything went smoothly. | Everything went smoothly. | Everything went smoothly. | Everything went smoothly. | Everything went smoothly.
Ghada | What did you you do yesterday? | Break | Enhanced database schema | Enhanced database schema | Tested database schema | Tested data flow
| What are doing today? | Enhancing database schema | Enhancing database schema | Test database schema | Test data flow | Complet documentation
| Is there anything blocking you? | Database problem | Database problem | Everything went smoothly. | Everything went smoothly. | Everything went smoothly.
Albandri | What did you you do yesterday? | Break | Enhanced database schema | Enhanced database schema | Tested database schema | Tested data flow
| What are doing today? | Enhancing database schema | Enhancing database schema | Test database schema | Test data flow | Complet documentation
| Is there anything blocking you? | Database problem | Database problem | No blockers | No blockers | No blockers

## WEEK 7
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?