## Blank Sprint Backlog
SPRINT BACKLOG 1
CURRENT DATE | SPRINT START DATE | TOTAL ASSIGNED HOURS |  | HOURS USED |  | HOURS REMAINING
2025-10-19 | 2025-10-13 | 62 |  | 51 |  | 11
SPRINT GOAL | The team aims to develop the core user features of the Hire Hub platform, focusing on registration, login, and job posting.
User Stories and Tasks | ASSIGNED TO | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14
User Registration (US-001) |  | 0 | 0 | 0
Design Registration Form UI | Joud AL-SHAHRANI | 8 | 8 | 0 | DAY 1: 4; DAY 2: 4; DAY 3: 0; DAY 4: 0; DAY 5: 0; DAY 6: 0; DAY 7: 0
Implement Email Validation | Joud AL-SHAHRANI | 6 | 5 | 1 | DAY 1: 1; DAY 2: 2; DAY 3: 2; DAY 4: 0; DAY 5: 0; DAY 6: 0; DAY 7: 0
Create User Database Schema | Jadel Alsaeri | 8 | 8 | 0 | DAY 1: 0; DAY 2: 1; DAY 3: 3; DAY 4: 4; DAY 5: 0; DAY 6: 0; DAY 7: 0
Setup Registration API | Jadel Alsaeri | 10 | 5 | 5 | DAY 1: 2; DAY 2: 0; DAY 3: 1; DAY 4: 2; DAY 5: 0; DAY 6: 0; DAY 7: 0
User Login (US-002) |  | 0 | 0 | 0
Design Login Page UI | Ghada Altemyat | 6 | 5 | 1 | DAY 1: 0; DAY 2: 2; DAY 3: 1; DAY 4: 2; DAY 5: 0; DAY 6: 0; DAY 7: 0
Implement Authentication Logic | Ghada Altemyat | 12 | 9 | 3 | DAY 1: 0; DAY 2: 0; DAY 3: 0; DAY 4: 3; DAY 5: 3; DAY 6: 3; DAY 7: 0
Setup Session Management | Albandri Alsaadoon | 8 | 7 | 1 | DAY 1: 2; DAY 2: 3; DAY 3: 2; DAY 4: 0; DAY 5: 0; DAY 6: 0; DAY 7: 0
Add Remember Me Feature | Albandri Alsaadoon | 4 | 4 | 0 | DAY 1: 0; DAY 2: 2; DAY 3: 2; DAY 4: 0; DAY 5: 0; DAY 6: 0; DAY 7: 0
Password Recovery (US-003) |  | 0 | 0 | 0
Design Password Reset Page | Ghada Altemyat | 5 | 4 | 1 | DAY 1: 2; DAY 2: 0; DAY 3: 0; DAY 4: 2; DAY 5: 0; DAY 6: 0; DAY 7: 0
Implement Email Sending Service | Jadel Alsaeri | 10 | 10 | 0 | DAY 1: 0; DAY 2: 0; DAY 3: 0; DAY 4: 3; DAY 5: 4; DAY 6: 3; DAY 7: 0
Create Reset Token System | Albandri Alsaadoon | 8 | 6 | 2 | DAY 1: 0; DAY 2: 0; DAY 3: 0; DAY 4: 1; DAY 5: 3; DAY 6: 2; DAY 7: 0
Test Password Reset Flow | Joud AL-SHAHRANI | 4 | 4 | 0 | DAY 1: 2; DAY 2: 0; DAY 3: 2; DAY 4: 0; DAY 5: 0; DAY 6: 0; DAY 7: 0
Create Job Seeker Profile (US-004) |  | 0 | 0 | 0
Design Profile Creation Form | Albandri Alsaadoon | 10 | 7 | 3 | DAY 1: 0; DAY 2: 3; DAY 3: 4; DAY 4: 0; DAY 5: 0; DAY 6: 0; DAY 7: 0
Implement Personal Info Section | Jadel Alsaeri | 8 | 8 | 0 | DAY 1: 0; DAY 2: 0; DAY 3: 0; DAY 4: 5; DAY 5: 3; DAY 6: 0; DAY 7: 0
Add Work Experience Section | Ghada Altemyat | 10 | 8 | 2 | DAY 1: 0; DAY 2: 3; DAY 3: 2; DAY 4: 0; DAY 5: 3; DAY 6: 0; DAY 7: 0
Add Education Section | Joud AL-SHAHRANI | 8 | 6 | 2 | DAY 1: 0; DAY 2: 0; DAY 3: 0; DAY 4: 3; DAY 5: 0; DAY 6: 3; DAY 7: 0
Add Skills Section | Albandri Alsaadoon | 6 | 3 | 3 | DAY 1: 0; DAY 2: 0; DAY 3: 3; DAY 4: 0; DAY 5: 0; DAY 6: 0; DAY 7: 0
Profile Completion Indicator | Joud AL-SHAHRANI | 5 | 5 | 0 | DAY 1: 0; DAY 2: 0; DAY 3: 0; DAY 4: 0; DAY 5: 5; DAY 6: 0; DAY 7: 0
Basic Job Search (US-007) |  | 0 | 0 | 0
Design Search Bar UI | Albandri Alsaadoon | 6 | 6 | 0 | DAY 1: 3; DAY 2: 0; DAY 3: 3; DAY 4: 0; DAY 5: 0; DAY 6: 0; DAY 7: 0
Implement Search Algorithm | Albandri Alsaadoon | 12 | 11 | 1 | DAY 1: 0; DAY 2: 5; DAY 3: 0; DAY 4: 3; DAY 5: 0; DAY 6: 3; DAY 7: 0
Display Search Results | Jadel Alsaeri | 8 | 4 | 4 | DAY 1: 0; DAY 2: 0; DAY 3: 0; DAY 4: 0; DAY 5: 4; DAY 6: 0; DAY 7: 0
Add Pagination | Jadel Alsaeri | 5 | 5 | 0 | DAY 1: 0; DAY 2: 0; DAY 3: 2; DAY 4: 0; DAY 5: 0; DAY 6: 0; DAY 7: 3
Post Job Listing (US-012) |  | 0 | 0 | 0
Design Job Posting Form | Ghada Altemyat | 10 | 8 | 2 | DAY 1: 0; DAY 2: 0; DAY 3: 0; DAY 4: 0; DAY 5: 1; DAY 6: 2; DAY 7: 5
Implement Rich Text Editor | Ghada Altemyat | 8 | 6 | 2 | DAY 1: 0; DAY 2: 0; DAY 3: 3; DAY 4: 0; DAY 5: 1; DAY 6: 2; DAY 7: 0
Create Job Posting API | Joud AL-SHAHRANI | 10 | 8 | 2 | DAY 1: 0; DAY 2: 2; DAY 3: 0; DAY 4: 2; DAY 5: 0; DAY 6: 0; DAY 7: 4
Add Job Preview Feature | Joud AL-SHAHRANI | 6 | 4 | 2 | DAY 1: 0; DAY 2: 0; DAY 3: 0; DAY 4: 0; DAY 5: 2; DAY 6: 0; DAY 7: 2
Implement Draft Save | Ghada Altemyat | 5 | 5 | 0 | DAY 1: 3; DAY 2: 0; DAY 3: 0; DAY 4: 0; DAY 5: 0; DAY 6: 0; DAY 7: 2
|  | 0 | 0 | 0
TOTAL |  | 62 | 51 | 11

## Blank Sprint Backlog (2)
SPRINT BACKLOG 2
CURRENT DATE | SPRINT START DATE | TOTAL ASSIGNED HOURS |  | HOURS USED |  | HOURS REMAINING
20/11/2025 12:01:09 AM | 2025-02-12 00:01 | 37 |  | 35 |  | 2
SPRINT GOAL | 16/11/2025
User Stories and Tasks | ASSIGNED TO | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14
User Story US-003: Enhanced Password Recovery |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.1 Task Name: Design Password Recovery Options UI | Albandri Alsadon | 6 | 5 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.2 Implement Phone Number Verification | Ghada Alemayat | 10 | 9 | 1 | 2 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Task1.3 Create Security Questions System | Jadel Alsaeri | 8 | 8 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.4Integrate SMS Service for OTP | Ghada Alemayat | 8 | 8 | 0 | 3 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.5: Test All Recovery Methods | Joud AlShahrani | 5 | 5 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 – Save Job Feature |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.1 Design Save Job Icon/Button | Albandri Alsadon | 4 | 4 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.2 Create Saved Jobs Database Schema | Jadel Alsaeri | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.3 Implement Save/Unsave Functionality | Ghada Alemayat | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.4 Build Saved Jobs Dashboard Section | Albandri alsadon | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.5 Test Save Job Feature | Ghada Alemayat | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 – Resume Upload |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.1 Design Resume Upload Interface | Albandri Alsadon | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.2 Implement File Upload Functionality | Ghada Alemayat | 8 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.3 Create File Storage System | Jadel Alsaeri | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.4 Add Resume Preview Feature | Albandri Alsadon | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.5 Test File Upload and Validation | Joud AlShahrani | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 – Profile Update |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.1 Design Edit Profile UI | Albandri Alsadon | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.2 Implement Profile Update API | Jadel Alsaeri | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.3: Add Form Validation | Ghada Alemayat | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.4 Test Profile Update Flow | Joud AlShahrani | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 – Application Filtering |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.1 Design Filter UI Components | Albandri Alsadon | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.2 Implement Filter Logic | Jadel Alsaeri | 10 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.3 Create Filter API Endpoints | Ghada Alemayat | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.4 Test Filtering Functionality | Joud AlShahrani | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 – Job Application Tracking |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.1 Design Application Tracking Dashboard | Albandri Alsadon | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.2 Create Application Status Database | Jadel Alsaeri | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.3 Implement Status Update Logic | Ghada Alemayat | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.4 Build Timeline View Component | Albandri Alsadon | 8 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.5 Add Filter by Status Feature | Jadel Alsaeri | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.6 Test Application Tracking System | Joud AlShahrani | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 – Employer Notification System |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.1 Design Notification Center UI | Albandri Alsadon | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.2 Create Notification Database Schema | Jadel Alsaeri | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.3 Implement In-App Notification System | Ghada Alemayat | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
Task 1.4 Integrate Email Notification Service | Ghada Alemayat | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0
Task 1.5 Build Notification Badge Component | Albandri Alsadon | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3
Task 1.6 Add Mark as Read/Delete Features | Jadel Alsaeri | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 0
Task 1.7 Test Notification System | Joud AlShahrani | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2
TOTAL |  | 37 | 35 | 2