## BURNDOWN CHART phases2
BURNDOWN CHART
Days | Goal | Done | Goal velocity | Remaining
0 | 0 | 0 | 504 | 500
1 | 36 | 25 | 468 | 475
2 | 36 | 30 | 432 | 445
3 | 36 | 32 | 396 | 413
4 | 36 | 36 | 360 | 377
5 | 36 | 38 | 324 | 339
6 | 36 | 38 | 288 | 301
7 | 36 | 40 | 252 | 261
8 | 36 | 42 | 216 | 219
9 | 36 | 44 | 180 | 175
10 | 36 | 46 | 144 | 129
11 | 36 | 46 | 108 | 83
12 | 36 | 43 | 72 | 40
13 | 36 | 25 | 36 | 15
14 | 36 | 15 | 0 | 0
Note on B8: stakeholdermap.com: Change the timescale to suit you needs e.g. Sprint or Iteration.
Note on C8: stakeholdermap.com: Number of features or story points you plan to complete.
Note on F8: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.

## BURNDOWN CHART phases3
BURNDOWN CHART
Days | Goal | Done | Goal velocity | Remaining
0 | 0 | 0 | 600 | 600
1 | 24 | 18 | 576 | 582
2 | 24 | 22 | 552 | 560
3 | 24 | 25 | 528 | 535
4 | 24 | 20 | 504 | 515
5 | 24 | 28 | 480 | 487
6 | 24 | 26 | 456 | 461
7 | 24 | 30 | 432 | 431
8 | 24 | 27 | 408 | 404
9 | 24 | 34 | 384 | 370
10 | 24 | 29 | 360 | 341
11 | 24 | 33 | 336 | 308
12 | 24 | 28 | 312 | 280
13 | 24 | 25 | 288 | 255
14 | 24 | 30 | 264 | 225
15 | 24 | 27 | 240 | 198
16 | 24 | 32 | 216 | 166
17 | 24 | 28 | 192 | 138
18 | 24 | 24 | 168 | 114
19 | 24 | 31 | 144 | 83
20 | 24 | 28 | 120 | 55
21 | 24 | 29 | 0 | 26
Note on B8: stakeholdermap.com: Change the timescale to suit you needs e.g. Sprint or Iteration.
Note on C8: stakeholdermap.com: Number of features or story points you plan to complete.
Note on F8: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME | Hire Hub – Job Search Website
PROJECT MANAGER | Dr. Mai Alduailij
DATE | 2025-10-26
VERSION | 1

## INSTRUCTIONS
Instructions
Days
Change this to the timescale that you want to appear at the bottom of the chart (the x axis).
Goal or target
Enter the number of features/story points that you plan to achieve in each time period. This forms the yellow line showing goal velocity on the chart.
Done or actual
Record how many features/story points that you actually achieve.
Goal or target velocity
This is a calculated field that counts down the target points to zero (completion of the project). It forms the left side of the chart (the y axis).
Remaining
This is a calculated field that simply deducts Done from Remaining. It is the blue line showing the actual burndown rate on the chart.